## Sheet1
[6 empty] | Phase 1 |  | Phase 2 |  | Phase 3 |  | Phase 4 |  | Phase 5 |  | Phase 6 |  | Phase 7
Team | Human Resource | Total person | Per month Salary | Cost per year | Total Cost | Man month | Effort | Man months | Effort | Man months | Effort | Man months | Effort | Man months | Effort | Man months | Effort | Man months | Effort
| Project manager | 1 | 6666.6667 | 80000 | 80000 | 1 | 6666.6667 | 1 | 6666.6667 | 4 | 26666.6667 | 2 | 13333.3333 | 2 | 13333.3333 | 1 | 6666.6667 | 1 | 6666.6667
Development Team | NLP/Speech Recognition Specialists | 3 | 10000 | 120000 | 360000 |  | 0 |  | 0 | 4 | 120000 | 2 | 60000 |  | 0 |  | 0 |  | 0
| Solution Architect | 1 | 10000 | 120000 | 120000 |  | 0 | 1 | 10000 | 4 | 40000 | 2 | 20000 |  | 0 |  | 0 |  | 0
Development Team | ML/DL Engineers/Developers | 2 | 10000 | 120000 | 240000 |  | 0 |  | 0 | 4 | 80000 | 2 | 40000 | 2 | 40000 | 1 | 20000 | 1 | 20000
Development Team | UI/UX Designers | 2 | 8333.3333 | 100000 | 200000 |  | 0 |  | 0 |  | 0 | 2 | 33333.3333 | 2 | 33333.3333 | 1 | 16666.6667 |  | 0
Development Team | Integration Specialists | 2 | 9166.6667 | 110000 | 220000 |  | 0 |  | 0 |  | 0 | 2 | 36666.6667 |  | 0 |  | 0 |  | 0
Total for the core development team |  | 11 | 0 |  | 1140000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
QA Team | QA Engineer | 2 | 9166.6667 | 110000 | 220000 |  | 0 |  | 0 |  | 0 | 2 | 36666.6667 | 2 | 36666.6667 | 1 | 18333.3333 |  | 0
Deployment and Itegrarion | Deployment Specialist | 1 | 9166.6667 | 110000 | 110000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 9166.6667 | 1 | 9166.6667
Training and Documentation | Training Specialist | 1 | 7500 | 90000 | 90000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Training and Documentation | Documentation Specialist | 1 | 7500 | 90000 | 90000 | 1 | 7500 | 1 | 7500 |  | 0 |  | 0 |  | 0 | 1 | 7500 | 1 | 7500
Support team | Support Engineers | 1 | 7500 | 90000 | 90000 | 1 | 7500 | 1 | 7500 |  | 0 |  | 0 |  | 0 | 1 | 7500 | 1 | 7500
Total for the miantainace team |  | 6 | 0 |  | 600000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Marketing team | Business Analyst | 1 | 6666.6667 | 80000 | 80000 | 1 | 6666.6667 | 1 | 6666.6667 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Marketing team | Marketing Manager | 1 | 8333.3333 | 100000 | 100000 | 1 | 8333.3333 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Marketing team | Marketing Specialists | 1 | 7500 | 90000 | 90000 | 1 | 7500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total For the business team |  | 3 |  |  | 270000 | 6 | 44166.6667 | 5 | 38333.3333 | 16 | 266666.6667 | 14 | 240000 | 8 | 123333.3333 | 7 | 85833.3333 | 5 | 50833.3333 | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Phase 6 | Phase 7
Total Human Resource Cost |  | 37 |  |  | 2010000
Technology | Per year cost
Hosting fees and licences | 20000
NLP and Speech Recognition Software | 50000
ML and DL Frameworks (e.g., TensorFlow, PyTorch) | 20000
Business Operations Integration Tools (e.g., APIs, SDKs) | 30000 |  |  | Total Cost | 2240000
UI Design and Development Tools (e.g., Adobe XD, Sketch) | 15000 |  |  | Office expenses | 336000
Testing and Bug Tracking Software | 25000 |  |  | Miscellaneous Expenses | 10000
Deployment and Integration Platforms | 40000 |  |  | Contingency | 20000
Documentation Tools (e.g., Confluence, Microsoft Word) | 10000 |  |  | Total Cost | 2606000
Collaboration and Communication Tools (e.g., Slack, Microsoft Teams) | 20000
Total Annual Technological Resources | 230000