## Sheet1
2024
| Project Start Date: |  | 2024-01-22 | [6 empty] | Jan | [9 empty] | Feb | [28 empty] | March | [23 empty] | Mar | [9 empty] | Apr | [26 empty] | May | [29 empty] | Aprik
| Project name: | AAICS Assistant |  |  |  |  | Week Starting: | time axis 2024-01-22 to 2024-06-09
WBS | Task | Assigned To |  | Start | End | %Done | Status | Resources
1 | Phase 1
1.1 | Research and Problem Identification | TeamWork |  |  |  | 100% | Completed | Human Resources
1.1.1 | Conduct domain research | TeamWork |  |  |  | 100% | Completed | Human Resources | bar: 2024-01-22 to 2024-01-25
1.1.2 | Identify specific problem or opportunity | TeamWork |  |  |  | 100% | Completed | Human Resources | bar: 2024-01-22 to 2024-01-25
1.1.3 | Analyze problem significance | TeamWork |  |  |  | 100% | Completed | Human Resources | bar: 2024-01-22 to 2024-01-25
1.1.4 | Problem Identified | TeamWork |  |  |  | 100% | Completed | Human Resources | bar: 2024-01-25
1.2.7 | Prepare Problem Identification Report | TeamWork |  |  |  | 100% | Completed | Human Resources | bar: 2024-01-25 to 2024-01-26
1.1.5 | Conduct kickoff meeting | TeamWork |  |  |  | 100% | Completed | Human Resources | bar: 2024-01-26
1.2 | Project Initiation |  |  |  |  | 100% | Completed | Human Resources
1.2.1 | Define project scope, objectives, and constraints | Sahran Khuwaja |  |  |  | 100% | Completed | Human Resources | bar: 2024-01-27 to 2024-02-04
1.2.2 | Identify stakeholders and their roles | Sahran Khuwaja |  |  |  | 100% | Completed | Human Resources | bar: 2024-01-27 to 2024-02-04
1.2.3 | Stakeholders Identified | TeamWork |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-04
1.2.4 | Create project charter | Sahran Khuwaja |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-01 to 2024-02-06
1.2.6 | Project Charter Approved | Sahran Khuwaja |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-06
1.3 | Market Analysis
1.3.1 | Target Audience Identification | Zahra Pezeshki |  |  |  | 100% | Completed | Human Resources | bar: 2024-01-27 to 2024-01-31
1.3.2 | Target Audience Identified | Zahra Pezeshki |  |  |  | 100% | Completed | Human Resources | bar: 2024-01-31
1.3.3 | Conduct demographic and psychographic analysis | Zahra Pezeshki |  |  |  | 100% | Completed | Human Resources | bar: 2024-01-31 to 2024-02-03
1.3.4 | Competitor Analysis | Omnia Alam/Yug Ritesh |  |  |  | 100% | Completed | Human Resources | bar: 2024-01-27 to 2024-02-07
1.3.5 | Competitor Analysis Completed | Omnia Alam/Yug Ritesh |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-07
1.3.6 | Business values Report | Zahra Pezeshki |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-09
1.3.6 | Business values Report Completed | Zahra Pezeshki |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-09
1.3.7 | Prepare Market Analysis Report | Omnia Alam/Yug Ritesh |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-09 to 2024-02-11
1.3.8 | Phase 1 submission | TeamWork |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-11
1.4 | Pitch Presentation Preparation
1.4.1 | Gather materials for presentation | TeamWork |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-12 to 2024-02-14
1.4.2 | Create slides and visual aids | Zahra Pezeshki |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-14 to 2024-02-15
1.4.3 | Rehearse presentation | Zahra Pezeshki |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-15
1.4.4 | Presentation Material Prepared | Zahra Pezeshki |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-15
1.4.5 | Pitch Presentation | Zahra Pezeshki | bar: 2024-02-16
2 | Phase2
2.1 | Feasibility | bar: 2024-02-23 to 2024-03-07
2.1.1 | Evaluate technical requirements | Sahran Khuwaja |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-23 to 2024-02-26
2.1.2 | Technical Feasibility Assessed | Sahran Khuwaja |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-26
2.1.3 | Assess operational impact | Sahran Khuwaja |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-26 to 2024-02-29
2.1.4 | Operational Feasibility Assessed | Sahran Khuwaja |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-29
2.1.5 | Estimate economic viability | Sahran Khuwaja |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-29 to 2024-03-02
2.1.6 | Economic Feasibility Determined | Sahran Khuwaja |  |  |  | 100% | Completed | Human Resources | bar: 2024-03-02
2.1.7 | Prepare Feasibility Study Report | Sahran Khuwaja |  |  |  | 100% | Completed | Human Resources | bar: 2024-03-03 to 2024-03-05
2.2 | Solution Proposal | bar: 2024-02-23 to 2024-03-03
2.2.1 | Develop software solution overview | Zahra Pezeshki |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-23 to 2024-02-24
2.2.2 | Software Solution Overview Defined | Zahra Pezeshki |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-24
2.2.3 | Define key features and functionalities | Zahra Pezeshki |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-24 to 2024-02-27
2.2.4 | Features and Functionalities Identified | Zahra Pezeshki |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-27
2.2.5 | Articulate benefits and impact | Zahra Pezeshki |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-25 to 2024-02-27
2.2.6 | Benefits and Impact Articulated | Zahra Pezeshki |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-27
2.2.7 | Prepare Software Solution Proposal | Zahra Pezeshki |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-27 to 2024-03-03
2.3 | Resource Allocation | Zahra Pezeshki |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-23 to 2024-02-27
2.3.1 | Allocate human resources | Zahra Pezeshki |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-23 to 2024-02-25
2.3.2 | Allocate technological resources | Zahra Pezeshki |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-24 to 2024-02-27
2.3.3 | Identify critical dependencies | Zahra Pezeshki |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-24 to 2024-02-27
2.3.4 | Resources Allocated | Zahra Pezeshki |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-27
2.4 | Risk Identification | bar: 2024-02-23 to 2024-03-06
2.4.1 | Identifying the risk | Yug Ritesh |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-23 to 2024-02-26
2.4.2 | Risks Identified | Yug Ritesh |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-26
2.4.3 | Solusion to mitgate the risk | Yug Ritesh |  |  |  | 100% | Completed | Human Resources | bar: 2024-02-26 to 2024-03-03
2.4.4 | Risk Mitigation Plan Developed | Yug Ritesh |  |  |  | 100% | Completed | Human Resources | bar: 2024-03-03
2.4.5 | Risk Identification Report | Yug Ritesh |  |  |  | 100% | Completed | Human Resources | bar: 2024-03-03 to 2024-03-06
2.5 | Budgeting | bar: 2024-03-03 to 2024-03-09
2.5.1 | Estimate project budget | Omnia Alam |  |  |  | 100% | Completed | Human Resources | bar: 2024-03-03 to 2024-03-05
2.5.2 | Budget Estimated | Omnia Alam |  |  |  | 100% | Completed | Human Resources | bar: 2024-03-05
2.5.3 | Break down budget into categories | Omnia Alam |  |  |  | 100% | Completed | Human Resources | bar: 2024-03-05 to 2024-03-07
2.5.4 | Allocate funds to each category | Omnia Alam |  |  |  | 100% | Completed | Human Resources | bar: 2024-03-07
2.5.5 | Budget Allocated | Omnia Alam |  |  |  | 100% | Completed | Human Resources | bar: 2024-03-07
2.5.6 | Prepare Software Development Budget | Omnia Alam |  |  |  | 100% | Completed | Human Resources | bar: 2024-03-07 to 2024-03-09
2.6 | End and Submission of Research | [5 empty] | Completed | Human Resources | bar: 2024-03-09
2.7 | Presentation Preparation | bar: 2024-03-16 to 2024-04-12
2.7.1 | Gather materials for presentation | Project Manager |  |  |  | 0% | Not Started | bar: 2024-03-16 to 2024-03-24
2.7.2 | Create slides and visual aids | Project Manager |  |  |  | 0% | Not Started | bar: 2024-03-24 to 2024-04-04
2.7.3 | Rehearse presentation | Project Manager |  |  |  | 0% | Not Started | bar: 2024-04-04 to 2024-04-05
2.7.4 | Presentation Material Prepared | Project Manager |  |  |  | 0% | Not Started | bar: 2024-04-05
2.7.5 | Finalize Project Presentation and Justification document | Project Manager |  |  |  | 0% | Not Started | bar: 2024-04-09 to 2024-04-12
3 | Phase 3 | bar: 2024-03-09 to 2024-05-30
3.1 | Development | bar: 2024-05-01 to 2024-05-18
3.1.1 | Implement Enhanced NLP and Speech Recognition | NLP/Speech Recognition Specialists |  |  |  | 0% | Not Started | Development Team | Technological Resources | bar: 2024-03-09 to 2024-03-25; 2024-03-30 to 2024-05-01
3.1.2 | NLP and Speech Recognition Implementation | NLP/Speech Recognition Specialists |  |  |  | 0% | Not Started | Development Team | Technological Resources | bar: 2024-03-25; 2024-04-07; 2024-05-01
3.1.3 | Integrate Machine Learning and Deep Learning Technologies | ML/DL Engineers |  |  |  | 0% | Not Started | Development Team | Technological Resources | bar: 2024-03-30 to 2024-05-01
3.1.4 | ML and DL Integration | ML/DL Engineers |  |  |  | 0% | Not Started | Development Team | Technological Resources | bar: 2024-04-07; 2024-05-01
3.1.5 | Develop Business Operations Integrations | Integration Specialist |  |  |  | 0% | Not Started | bar: 2024-04-12 to 2024-05-01
3.1.6 | Business Operations Integration | Integration Specialist |  |  |  | 0% | Not Started | bar: 2024-05-01
3.1.7 | Design User Interface (UI) | UI/UX Designers |  |  |  | 0% | Not Started | bar: 2024-04-12 to 2024-05-01
3.1.8 | UI Design | UI/UX Designers |  |  |  | 0% | Not Started | bar: 2024-05-01
3.1.9 | Quality Control and Feedback Mechanism | QA Engineer |  |  |  | 0% | Not Started | bar: 2024-03-22 to 2024-03-25; 2024-04-06 to 2024-04-07; 2024-05-13 to 2024-05-18
3.1.10 | Ensure Scalability and Performance | QA Engineer |  |  |  | 0% | Not Started | bar: 2024-03-25; 2024-04-07; 2024-05-18
3.1.11 | Scalability and Performance Assurance | QA Engineer |  |  |  | 0% | Not Started | bar: 2024-05-04 to 2024-05-18
3.1.12 | Iteration | bar: 2024-03-09 to 2024-03-25; 2024-03-30 to 2024-04-07; 2024-04-12 to 2024-04-16; 2024-05-01 to 2024-05-18
3.2 | Testing and Quality Assurance
3.2.1 | Develop Test Plans and Test Cases | QA Engineer |  |  |  | 0% | Not Started | Quality Assurance Team | Development Team | bar: 2024-03-25 to 2024-03-30; 2024-04-07 to 2024-04-11; 2024-04-16 to 2024-04-19; 2024-05-18 to 2024-05-24
3.2.2 | Test Plan Development | QA Engineer |  |  |  | 0% | Not Started | Quality Assurance Team | Development Team | bar: 2024-03-30; 2024-04-11; 2024-04-19; 2024-05-24
3.2.3 | Execute Functional Testing | QA Engineer |  |  |  | 0% | Not Started | Quality Assurance Team | Development Team | bar: 2024-03-28 to 2024-03-30; 2024-04-09 to 2024-04-11; 2024-04-19 to 2024-04-21; 2024-05-24 to 2024-05-26
3.2.4 | Testing Execution | QA Engineer |  |  |  | 0% | Not Started | Quality Assurance Team | Development Team | bar: 2024-03-30; 2024-04-11; 2024-04-21; 2024-05-26
3.2.5 | Perform Usability Testing | QA Engineer |  |  |  | 0% | Not Started | Quality Assurance Team | Development Team | bar: 2024-03-29 to 2024-03-30; 2024-04-10 to 2024-04-11; 2024-04-19 to 2024-04-23; 2024-05-24 to 2024-05-28
3.2.6 | Conduct Performance Testing | QA Engineer |  |  |  | 0% | Not Started | Quality Assurance Team | Development Team | bar: 2024-03-30; 2024-04-11; 2024-04-23; 2024-05-28
3.2.7 | Implement Security Testing | QA Engineer |  |  |  | 0% | Not Started | Quality Assurance Team | Development Team | bar: 2024-03-28 to 2024-03-30; 2024-04-09 to 2024-04-11; 2024-04-21 to 2024-04-23; 2024-05-27 to 2024-05-29
3.2.8 | Address Bugs and Issues | QA Engineer |  |  |  | 0% | Not Started | Quality Assurance Team | Development Team | bar: 2024-03-29 to 2024-03-30; 2024-04-10 to 2024-04-11; 2024-04-22 to 2024-04-23; 2024-05-23 to 2024-05-29
3.2.9 | Bug Fixing | QA Engineer |  |  |  | 0% | Not Started | Quality Assurance Team | Development Team | bar: 2024-03-30; 2024-04-11; 2024-04-23; 2024-05-29
3.2.10 | Iteration |  |  |  |  | 0% | Not Started | bar: 2024-03-25 to 2024-03-30; 2024-04-07 to 2024-04-11; 2024-04-16 to 2024-04-23; 2024-05-18 to 2024-05-29
3.3 | Deployment and Integration
3.3.1 | Deploy AAICS System | Deployment Specialist |  |  |  | 0% | Not Started | Deployment and Integration Team | bar: 2024-04-20 to 2024-04-25; 2024-05-10 to 2024-05-16
3.3.2 | System Deployment | Deployment Specialist |  |  |  | 0% | Not Started | Deployment and Integration Team | bar: 2024-04-25; 2024-05-16
3.3.3 | Integrate with Existing Systems and Platforms | Integration Specialist |  |  |  | 0% | Not Started | Deployment and Integration Team | bar: 2024-04-22 to 2024-04-25; 2024-05-11 to 2024-05-18
3.3.4 | Integration with Existing Systems | Integration Specialist |  |  |  | 0% | Not Started | Deployment and Integration Team | bar: 2024-04-25; 2024-05-18
3.3.5 | Conduct Integration Testing | Integration Specialist |  |  |  | 0% | Not Started | Deployment and Integration Team | bar: 2024-04-23 to 2024-04-25; 2024-05-16 to 2024-05-18
3.3.6 | Integration Testing | Integration Specialist |  |  |  | 0% | Not Started | Deployment and Integration Team | bar: 2024-04-25; 2024-05-18
3.3.7 | Ensure Data Migration and Compatibility | Deployment Specialist |  |  |  | 0% | Not Started | Deployment and Integration Team | bar: 2024-05-14 to 2024-05-18; 2024-05-28 to 2024-05-30
3.3.8 | Validate System Functionality | Deployment Specialist |  |  |  | 0% | Not Started | Deployment and Integration Team | bar: 2024-05-14 to 2024-05-18; 2024-05-26 to 2024-05-30
3.3.9 | Validation of System Functionality | Deployment Specialist |  |  |  | 0% | Not Started | Deployment and Integration Team | bar: 2024-05-18; 2024-05-30
3.3.10 | Iteration |  |  |  |  | 0% | Not Started | Deployment and Integration Team | bar: 2024-04-20 to 2024-04-25; 2024-05-10 to 2024-05-18
3.4 | Training and Documentation
3.4.1 | Prepare Training Material for Users and Administrators | Training Specialist |  |  |  | 0% | Not Started | Training and Documentation Team | bar: 2024-05-02 to 2024-05-29
3.4.2 | Training Material Preparation | Training Specialist |  |  |  | 0% | Not Started | Training and Documentation Team | bar: 2024-05-29
3.4.3 | Conduct Training Sessions | Training Specialist |  |  |  | 0% | Not Started | Training and Documentation Team | bar: 2024-05-20 to 2024-05-29
3.4.4 | Training session conducted | Training Specialist | [5 empty] | Training and Documentation Team | bar: 2024-05-29
3.4.5 | Create User Manuals and Guides | Documentation Specialist |  |  |  | 0% | Not Started | Training and Documentation Team | bar: 2024-05-15 to 2024-05-29
3.4.6 | User Manuals and Guides Created | Documentation Specialist |  |  |  | 0% | Not Started | Training and Documentation Team | bar: 2024-05-29
3.4.7 | Develop Technical Documentation | Documentation Specialist | [5 empty] | Training and Documentation Team | bar: 2024-05-15 to 2024-05-29
3.4.8 | Documentation Development | Documentation Specialist |  |  |  | 0% | Not Started | Training and Documentation Team | bar: 2024-05-29
3.4.9 | Establish Support Channels | Documentation Specialist |  |  |  | 0% | Not Started | Training and Documentation Team | bar: 2024-05-08 to 2024-05-29
3.4.10 | Support Channels | Documentation Specialist |  |  |  | 0% | Not Started | Training and Documentation Team | bar: 2024-05-29
[6 empty] | 0% | Not Started
3.5 | Project Closure | bar: 2024-05-31 to 2024-06-09
3.5.1 | Review Project Performance against Objectives |  |  |  |  | 0% | Not Started | bar: 2024-05-31 to 2024-06-06
3.5.2 | Project Performance Review |  |  |  |  | 0% | Not Started | bar: 2024-06-06
3.5.3 | Document Lessons Learned |  |  |  |  | 0% | Not Started | bar: 2024-06-02 to 2024-06-07
3.5.4 | Lessons Learned Documented |  |  |  |  | 0% | Not Started | bar: 2024-06-07
3.5.5 | Handover Deliverables to Stakeholders |  |  |  |  | 0% | Not Started | bar: 2024-05-31 to 2024-06-04
3.5.6 | Deliverables Handover |  |  |  |  | 0% | Not Started | bar: 2024-06-04
3.5.7 | Celebrate Project Success |  |  |  |  | 0% | Not Started | bar: 2024-06-08 to 2024-06-09
3.5.8 | Project Success Celebration |  |  |  |  | 0% | Not Started | bar: 2024-06-09
3.5.9 | Conduct Post-Implementation Review |  |  |  |  | 0% | Not Started | bar: 2024-06-05 to 2024-06-09
3.5.10 | Post-Implementation Review |  |  |  |  | 0% | Not Started | bar: 2024-06-09
# | Resources |  |  | Quantity | Type
1 | Project Manager |  |  | 1 Person | Human Resources
2 | NLP/Speech Recognition Specialists |  |  | 3 Person | Development Team
3 | ML/DL Engineers |  |  | 2 Person | Development Team
4 | UI/UX Designers |  |  | 2 Person | Development Team
5 | Integration Specialists |  |  | 2 Person | Development Team
6 | QA Engineer |  |  | 1 person | Quality Assurance Team
7 | Deployment Specialist |  |  | 1 person | Deployment and Integration Team
8 | Integration Specialist |  |  | 1 person | Deployment and Integration Team
9 | Training Specialist |  |  | 1 person | Training and Documentation Team
10 | Documentation Specialist |  |  | 1 person | Training and Documentation Team
11 | Support Engineers |  |  | 2 persons | Support Team
12 | Business Analyst |  |  | 1 person | Marketing Team
13 | Marketing Manager |  |  | 1 person | Marketing Team
14 | Marketing Specialists |  |  | 2 person | Marketing Team
15 | Content Writer |  |  | 2 person | Marketing Team
16 | Graphic Designer |  |  | 2 person | Marketing Team
17 | NLP and Speech Recognition Software |  |  | Annually | Marketing Team
18 | ML and DL Frameworks (e.g., TensorFlow, PyTorch) |  |  | Annually | Technological Resources
19 | Business Operations Integration Tools (e.g., APIs, SDKs) |  |  | Annually | Technological Resources
20 | UI Design and Development Tools (e.g., Adobe XD, Sketch) |  |  | Annually | Technological Resources
21 | Testing and Bug Tracking Software |  |  | Annually | Technological Resources
22 | Deployment and Integration Platforms |  |  | Annually | Technological Resources
23 | Documentation Tools (e.g., Confluence, Microsoft Word) |  |  | Annually | Technological Resources
24 | Collaboration and Communication Tools (e.g., Slack, Microsoft Teams) |  |  | Annually | Technological Resources
25
| Resource Category |  | Listing of deliverables at each project phase
| Human Resources |  | Planning and Requirements Gathering: Project Charter, Requirements Document
| Development Team |  | Design and Architecture: System Design Document, Architecture Diagrams
| Quality Assurance Team |  | Development and Integration: MVP Prototype, Codebase
| Deployment and Integration Team |  | Testing and Quality Assurance: Test Plans, Test Reports
| Training and Documentation Team |  | Deployment and Training: Deployment Plan, Training Materials
| Support Team |  | Monitoring and Maintenance: Maintenance Plan, Bug Fix Releases
Marketing Team
Technological Resources
| Status List |  | Identification of critical dependencies
| Not Started |  | Availability of Stakeholders for Requirements Gathering
| In Progress |  | Timely Completion of Design and Architecture Phase for Development to Begin
| Completed |  | Testing Resources Allocated for QA Phase to Ensure Comprehensive Testing
⬥
Human Resource
Project Manager
NLP/Speech Recognition Specialists
ML/DL Engineers
UI/UX Designers
Integration Specialists
QA Engineer
Deployment Specialist
Integration Specialist
Training Specialist
Documentation Specialist
Support Engineers
Business Analyst
Marketing Manager
Marketing Specialists
Content Writer
Graphic Designer
1st Iteration
1st Iteration
2nd Iteration
2nd Iteration
2nd Iteration
2nd Iteration
1st Iteration
2nd Iteration
3nd Iteration
3nd Iteration